## Sheet1
0. Purpose: This worksheet contains the estimated and actual project data.
Student |  |  | Date |  |  |  | 1. Enter your name, and the date you started the programming assignment.
Program |  |  | Program # |  |  |  | 2. Include program name in cell B2, and assignment number in cell F2.
Instructor |  |  | Language |  |  |  | 3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
Program Size (LOC) |  |  | Actual | Last Program |  | To Date | Prior to development:
Base (B) |  | (counted) |  |  |  |  | 0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D) |  | (counted)
Modified (M) |  | (counted) |  |  |  |  | 1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A) |  | (T-B+D-R) | 0 | 0
Reused (R) |  | (counted) |  |  |  | 0 | 2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N) |  | (A+M) | 0 | 0 |  | 0
Total LOC (T) |  | (counted) |  |  |  | 0 | 3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
| LOC/Hr |  | - | - |  | -
After development:
Time in Phase (minutes) |  | Plan | Actual | Last Program | To Date | To Date % | 4. Measure your finished program total LOC, and enter the value into cell E13.
Planning |  |  |  |  | 0 | - | 5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design |  |  |  |  | 0 | -
Code |  |  |  |  | 0 | -
Compile |  |  |  |  | 0 | - | Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test |  |  |  |  | 0 | -
Postmortem |  |  |  |  | 0 | -
Total |  | 0 | 0 | 0 | 0 | 0%
Defects Injected |  |  | Actual | Last Program | To Date | To Date % | Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning |  |  |  |  | 0 | -
Design |  |  |  |  | 0 | -
Code |  |  |  |  | 0 | -
Compile |  |  |  |  | 0 | -
Test |  |  |  |  | 0 | - | Summary
Postmortem |  |  |  |  | 0 | -
Total Development |  |  | 0 | 0 | 0 | 0%
Defects Removed |  |  | Actual | Last Program | To Date | To Date %
Planning |  |  |  |  | 0 | -
Design |  |  |  |  | 0 | -
Code |  |  |  |  | 0 | -
Compile |  |  |  |  | 0 | -
Test |  |  |  |  | 0 | -
Postmortem |  |  |  |  | 0 | -
Total Development |  |  | 0 | 0 | 0 | 0%
After Development |  |  | 0 | 0 | 0
By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
(eSignature)