## Sheet1
				0. Purpose: This worksheet contains the estimated and actual project data.
Student	Mauricio			Date	4/1/2016				1. Enter your name, and the date you started the programming assignment.
Program	03. TokenizingTelNumbs			Program #	3				2. Include program name in cell B2, and assignment number in cell F2.
Instructor	Paul Conrad			Language	Java				3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.

Program Size (LOC)				Actual	Last Program		To Date		Prior to development:
Base (B)			(counted)	0					0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0
Modified (M)			(counted)	0					1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	218	0
Reused (R)			(counted)	0			0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	218	0		218
Total LOC (T)			(counted)	218			218		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		79.2727272727	0		79.2727272727
				After development:
Time in Phase (minutes)			Plan	Actual	Last Program	To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning			30	10		10	6%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design			20	35		35	21%
Code			60	70		70	42%
Compile			0	0		0	0%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test			20	40		40	24%
Postmortem			20	10		10	6%
Total			150	165	0	165	100%

Defects Injected				Actual	Last Program	To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning				4		4	36%
Design				4		4	36%
Code				0		0	0%
Compile				0		0	0%
Test				3		3	27%		Summary
Postmortem				0		0	0%		I Spent about 3 Hours give or take on this assignment / This assignment called for a telephone number to be input by a user, to then be printed as tokens on the terminal. / My method for solving this problem, was to first sanatize the user inputs, so that when the Program was to tokenize the phone number, nothing would go astray. / I achived this by allowing all inputs by the user. This way I can discars his unwanted inputs to only be left with a Phone number. / By inputing all the user inputs into a string, I then used regular expressions to discard anything that was not a number. / Aftet that, we need to check 2 things to assure that the inputs are indeed a telephone number: / 1. The area code of the number cannot begin with a 0 or a 1. / 2. the phone number must be exactly 10 digits. / I executed the first, thinking that it would be faster to fail that test, than to go through the entirer sanatized input. / Remember that if the user inputs, more than 10 digits, I would atleast have to find the first 10, then test the first digit for a 1 or a 0. / Once theise test paessed, we can prepare the phone number for tokenizing. / I take the string of 10 digits, and put it in another string in the format of "(XXX)XXX-XXXX" / This allows me to simply tokenize at all non numeric numbers not including spaces. / To not get a value of 4 tokens, I temporarly place the formated string into a temporarie string, and replacing the open parentasies "(" with a space. / Now when I call my tokens, i will get splits at the closed parentasies ")" and the minus sign "-". It is a bit of cheating, but the way I was calling my token, / I kept getting 4 tokens, the first one being a blank. This was the only way I was able to solve my problem.
Total Development				11	0	11	100%

Defects Removed				Actual	Last Program	To Date	To Date %
Planning				0		0	0%
Design				2		2	9%
Code					0	0%
Compile				0		0	0%
Test				10		10	45%
Postmortem				10		10	45%
Total Development				22	0	22	100%
After Development				-11	0	-11

				Mauricio S. Perez			By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)