## Sheet1
				0. Purpose: This worksheet contains the estimated and actual project data.
Student	Mauricio			Date	4/1/2016				1. Enter your name, and the date you started the programming assignment.
Program	03. TokenizingTelNumbs			Program #	3				2. Include program name in cell B2, and assignment number in cell F2.
Instructor	Paul Conrad			Language	Java				3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.

Program Size (LOC)				Actual	Last Program		To Date		Prior to development:
Base (B)			(counted)	34	0				0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	20	0
Modified (M)			(counted)	15	0				1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	180	218
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	195	218		413
Total LOC (T)			(counted)	375			375		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		41.7857142857	46.7142857143		55.6853932584
				After development:
Time in Phase (minutes)			Plan	Actual	Last Program	To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning			30	100	10	110	25%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design			30	40	35	75	17%
Code			60	120	70	190	43%
Compile			0	0	0	0	0%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test			20	20	40	60	13%
Postmortem			20	0	10	10	2%
Total			160	280	165	445	100%

Defects Injected				Actual	Last Program	To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning				0	4	4	36%
Design				0	4	4	36%
Code				0	0	0	0%
Compile				0	0	0	0%
Test				0	3	3	27%		Summary
Postmortem				0	0	0	0%		This assignment took me about 2 hours, plus 2 hours of studying the I/O in the chapters. / 34 - LSLINES EQUATION / 180 - Read Text File / This Assignment was a bit tricky. New material always is when you dont understand whats going on 100% / We were tasked with opening an existing set of data, and creating a linear equation with it: Y=MX+B / Using the x and y data points, we were to not only read in the data, print it, manipulated to find the components of the linear equation, / we were asked to print the linear equation at the end of the data read. / This was tricky because we had to gather all the data while reading in new data, and keeping track of the components that would help us find the slope M, and the y intercept B. / I was not sucessfull in writing the final equation out into a file, but was able to print it to the terminal. / I also don't know if the formula for finding the linear equation was incorrect in the instructions, I did my math on an / excel spreadsheet, and could not come up with the numbers expected, but my spreadsheet dose match my data from the console. / See extras for spreadsheet.
Total Development				0	11	11	100%

Defects Removed				Actual	Last Program	To Date	To Date %
Planning				0	0	0	0%
Design				1	2	3	13%
Code				0	0	0	0%
Compile				0	0	0	0%
Test				0	10	10	43%
Postmortem				0	10	10	43%
Total Development				1	22	23	100%
After Development				-1	-11	-12

				Mauricio S. Perez			By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)