## Sheet1
				0. Purpose: This worksheet contains the estimated and actual project data.
Student	Mauricio S. Perez			Date	3/2/2016				1. Enter your name, and the date you started the programming assignment.
Program	12.14: Guess-a-number Game			Program #	1				2. Include program name in cell B2, and assignment number in cell F2.
Instructor	Paul Conrad			Language	Java				3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.

Program Size (LOC)				Actual	Last Program		To Date		Prior to development:
Base (B)			(counted)	160	0				0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	158	0
Modified (M)			(counted)	0	0				1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	154	0
Reused (R)			(counted)	2	0		2		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	154	0		154
Total LOC (T)			(counted)	158	0		158		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		78.304421149	0		78.304421149
				After development:
Time in Phase (minutes)			Plan	Actual	Last Program	To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning			20	30		30	25%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design			10	23		23	19%
Code			30	45		45	38%
Compile			0.05	0.001		0.001	0%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test			20	20		20	17%
Postmortem			5	0		0	0%
Total			85.05	118.001	0	118.001	100%

Defects Injected				Actual	Last Program	To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning				5	0	5	28%
Design				1	0	1	6%
Code				1	0	1	6%
Compile				1	0	1	6%
Test				10	0	10	56%		Summary
Postmortem				0	0	0	0%		This project was simple enough but I made it more complicated than it had to be. / First off: I understood the part where we were to use Jlables and Jtext Files to change visuals and text. I wanted to implement a god mode feature that shows the , but was not successful in Implementing it. / Second: The planing was not to long, about 20 minutes to dream up, with the known methods of class notes and book knowledge. What kills your time is moving stuff around and labeling and editing text so as to find the right variables in the generated code. That took way more than planing. / Third: This File is pretty straight forward, but I forgot how to calculate Lines of Code (LOC). Om essence I'm not sure I filled it out correctly.
Total Development				18	0	18	100%

Defects Removed				Actual	Last Program	To Date	To Date %
Planning				2	0	2	40%
Design				1	0	1	20%
Code				0.001	0	0.001	0%
Compile				1	0	1	20%
Test				1	0	1	20%
Postmortem				0	0	0	0%
Total Development				5.001	0	5.001	100%
After Development				12.999	0	12.999

				Mauricio S. Perez			By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)